Introduction

BrewCode POS project is an attempt to supply a streamlined Point of Sale system for the coffee shops with its aim being to improve order processing, payment manager as well as inventory management. This Project Management Plan describes the goal, the deliverables and the advantages of the BrewCode POS system, thus directing a structured way to achieve successful implementation.

The project’s key outputs are user-friendly POS interface, real-time inventory updates and role based user access for café personnel. Such capabilities endeavour to eliminate manual mistakes, streamline transactions, streamline processes and enhance the full productivity. With inventory and sales tracking streamlined by BrewCode POS, café managers gain valuable insights and greater management over a day-to-day basis.

This project plan gives an outline of the project’s objectives, major functionalities and anticipated advantage. Although technical details and timeline of the project are mentioned in later sections of this document, the introduction will be a roadmap to realize the main purpose and expected results of the BrewCode POS system.

Project Management Approach

The BrewCode POS project will utilize the Waterfall Process Model, which follows a linear and sequential development lifecycle. This model is best suited for the project as it ensures clarity in requirements, structured planning, and disciplined execution. Each phase will be completed before the next begins, minimizing risks associated with scope changes and ensuring clear deliverables at each stage.

Project Lifecycle Phases:

Requirements Gathering (Week 1–2):

Conduct detailed interviews with café stakeholders and document system requirements.

System Design (Week 1–2):

Translate requirements into wireframes and technical design specifications.

Development (Week 3–4):

Implement the core modules including order management, inventory tracking, and payment processing.

Testing (Week 5–6):

Execute functionality and usability tests based on real café transactions.

Deployment and Training (Week 7–8):

Deploy the system to the café and train staff on system usage.

Governance Structure & Key Roles:

Project Manager: Oversees the overall project plan, timeline, and communication with stakeholders. Ensures that each phase meets quality and time requirements.

UI/UX Designer: Creates the system’s user-friendly interface using tools like Figma and ensures an intuitive experience for café staff.

Backend Developer: Develops the application logic and database integration using Visual Studio Code.

Tester: Conducts system and user acceptance testing to validate functionality.

Trainer: Delivers hands-on system training to café staff post-deployment.

Development Tools:

Visual Studio Code (VS Code): Primary IDE for development.

Notion: Used for documentation, progress tracking, and internal communication.

(Other tools may be added as needed during development.)

Project Scope

Project Title: BrewCode POS – “Brewing Efficiency: A POS That Puts Your Café in Control”

Goals:

- Streamline café operations.

- Automate ordering, payments, and inventory updates.

Deliverables:

- User-friendly POS interface.

- Inventory management with real-time updates.

- Role-based access for staff and management.

- Payment processing module.

- Sales reporting and dashboard.

- Deployment, documentation, and staff training.

Boundaries:

- Included: Laptop-based POS system, real-time inventory, reporting tools, basic user authentication.

- Excluded: Mobile POS apps, loyalty programs, accounting integration.

Acceptance Criteria:

- Final product passes testing, meets functional specs, and is approved by the Café Owner based on system demo and documentation.

Milestone List

| Milestone | Description | Timeline | Responsible |
| --- | --- | --- | --- |
| - Requirements Gathering | Conduct interviews and finalize user/system requirements. | Week 1 | Project Manager |
| - System Design Completion | Create UI wireframes and technical architecture. | Week 2 | UI/UX Designer, Devs |
| - Order Module Development | Develop and test order input and editing functionality. | Week 3 | Backend Developer |
| - Inventory and Payment Integration | Integrate real-time inventory updates and payment recording. | Week 4 | Backend Developer |
| - Internal Testing | Perform functional and bug testing using sample transactions. | Week 5 | Tester |
| - User Acceptance Testing (UAT) | Simulate real-world café use to ensure the system meets requirements. | Week 6 | Tester, Project Manager |
| - System Deployment | Deploy the POS system to the café environment. | Week 7 | Project Manager, Devs |
| - Staff Training and Final Handover | Train café staff and officially hand over the system. | Week 8 | Trainer, Project Manager |

Schedule Baseline and Work Breakdown Structure

The Work Breakdown Structure for the BrewCode POS Project is made of work packages that are at least 2 hours of work and do not exceed 40 hours of work. The work packages are developed through close collaboration of project team members and project stakeholders, with guidance of the project manager.

The WBS Dictionary outlines tasks in the BrewCode POS Project. It defines each task, resources, and deliverables. Each task described in the WBS Dictionary will help in resource allocation, task execution, and ensuring that the deliverables do align with project requirements.

The BrewCode POS schedule is derived from the WBS and Project Charter, with team input. It is maintained as an MS Excel Gantt Chart by the Project Manager and baselined after sponsor approval. Any proposed changes to the schedule will follow the BrewCode change control process. If established boundary controls may be exceeded, a change request will be submitted to the Project Manager. The Project Manager and team will determine the impact of the change on the schedule, cost, resources, scope, and risks. If it is determined that the impacts will exceed the boundary conditions, then the change will be forwarded to the Project Sponsor for review and approval. The BrewCode boundary conditions are:

- CPI (Cost Performance Index) less than 0.8 or greater than 1.2

- SPI (Schedule Performance Index) less than 0.8 or greater than 1.2

If the change is approved by the Project Sponsor, it will be implemented by the Project Manager, who will update the schedule and all documentation and communicate the change to all stakeholders in accordance with the Change Control Process.

Change Management Plan

The following steps comprise the change control process for the BrewCode POS project and will be strictly followed:

Step #1: Identify the Need for a Change (Any Stakeholder)

The requestor submits a completed BrewCode Change Request Form to the Project Manager.

- Form must include:

  - Description of the proposed change.

  - Reason for the change.

  - Initial impact assessment (if known).

Step #2: Log Change in the Change Request Register (Project Manager)

The Project Manager logs the change in the BrewCode Change Request Register (shared document).

- Assign a unique ID and track status (Pending/Approved/Rejected).

Step #3: Conduct an Evaluation of the Change (Project Manager, Requestor)

The Project Manager leads a team evaluation of the change’s impact on:

  - Schedule (timeline delays).

  - Cost (additional resources/budget).

  - Scope (alignment with original requirements).

  - Quality/Risks (technical feasibility, user experience).

- Findings are documented in a Change Impact Report.

Step #4: Submit Change Request to Change Control Board (CCB) (Project Manager)

The Project Manager submits the Change Request Form, Impact Report, and recommendations to the CCB for review.

Step #5: Change Control Board Decision (CCB)

The CCB reviews the change request and supporting documents.

- CCB Members:

  - Chair: Project Sponsor (Client/Café Owner).

  - Members: Project Manager, Project Team Members.

- Decision options: Approve, Reject, or Request Modifications.

- Final decision is recorded in the Change Request Register.

Step #6: Implement Change (Project Manager)

Approved:

- Project Manager updates project documentation (timeline, budget, scope).

- Developers implement changes; Testers validate functionality.

- Trainer updates user guides and conducts staff training (if needed).

- Project Manager communicates changes to all stakeholders.

Rejected:

- Project Manager informs the requestor with a rationale for rejection.

Any team member or stakeholder can submit a change request. The Project Sponsor leads the Change Control Board and must approve adjustments that affect scope, cost, or schedule. All changes (accepted or rejected) are recorded in the Change Request Register and tracked until completion. Critical bugs or errors may not require prior approval, but they must be reviewed and documented by the Change Control Board after implementation.

Communications Management Plan

#### 1.  Communication Requirements Based on Roles

| Role | Communication Needs |
| --- | --- |
| Project Manager | Oversees project progress, risks, and stakeholder alignment. |
| Designer | Needs feedback on design elements and usability. |
| Developer | Requires updates on system logic, database structure, and integration. |
| Tester | Needs reports on bugs, test results, and performance. |
| Café Owner (Client) | Requires updates on project progress, key milestones, and demonstrations. |
| Café Staff (End Users) | Needs training, troubleshooting guides, and system updates. |

#### 2. What Information Will Be Communicated

- Project Progress Updates: Status reports, completed tasks, and next steps.

- Technical Updates: System design changes, development issues, and bug reports.

- Financial Updates: Budget utilization and any financial concerns.

- Training Materials: User guides and training schedules for end users.

- Risk and Issue Reports: Identified risks, mitigation strategies, and resolutions.

#### 3. How the Information Will Be Communicated

- Meetings (Virtual/In-person): For progress updates, feedback sessions, and demonstrations.

- Emails: For formal reports, approvals, and milestone summaries.

- Project Management Tools (Trello, Jira): For task tracking and collaboration.

- Slack/Discord: For real-time communication within the development team.

- Google Drive/Notion: For document storage and easy access to shared materials.

#### 4. When Will Information Be Distributed

| Communication Type | Frequency |
| --- | --- |
| Daily Standup Meetings | Daily |
| Project Status Updates | Weekly |
| Client Update Meetings | Bi-weekly |
| Training Sessions | Before deployment |
| Budget Reviews | Monthly |

#### 5. Who Does the Communication

- Project Manager: Overall project updates, risk management, and financial reporting.

- UI/UX Designer: Shares design updates and collects feedback.

- Backend Developer: Communicates technical issues and progress.

- Tester: Reports on testing results and system performance.

- Trainer: Conducts training sessions for café staff.

#### 6. Who Receives the Communication

- Project Team (Developers, Designers, Testers) receive daily updates.

- Café Owner (Client) receives milestone updates and demonstrations.

- Café Staff (End Users) receive training and system guides.

- Stakeholders/Investors receive monthly financial reports if applicable.

#### 7. Communications Conduct

- Maintain clear, concise, and professional communication.

- Encourage open feedback and discussions.

- Document all major decisions and approvals.

- Ensure confidentiality of sensitive project information.

### Cost Management Plan

#### 1. Identifies Who is Responsible for Managing Costs

- Project Manager is responsible for overseeing the project budget, tracking expenses, and ensuring cost efficiency.

#### 2. Identifies Who Has the Authority to Approve Changes to the Project or Its Budget

- The Project Sponsor or Café Owner (Client) has final authority over budget changes.

- The Project Manager can approve minor budget adjustments within a predefined limit.

#### 3. How Cost Performance is Quantitatively Measured and Reported Upon

- Budget Variance (BV): Measures the difference between planned and actual costs.

- Cost Performance Index (CPI): Determines cost efficiency based on earned value vs. actual spending.

- Percentage of Completion: Tracks how much of the project has been completed within budget.

4. Report Formats, Frequency, and Recipients

| Report Type | Format | Frequency | Recipients |
| --- | --- | --- | --- |
| Budget Status Report | PDF/Spreadsheet | Monthly | Client, Project Team |
| Expense Breakdown | Excel Sheet | Bi-weekly | Project Manager |
| Cost Report | Graph/Chart | As needed | Project Sponsor, Investors (if applicable) |
| Final Cost Summary | Formal Report | End of Project | Client, Stakeholders |

Procurement Management Plan

Objective:
 Define how the BrewCode POS project team will acquire necessary goods and services.

Procurement Items:

- Hardware: Laptops, optional cash drawers.

- Software: Development tools (e.g., Visual Studio Code), UI/UX design tools (e.g., Figma), databases (SQLite, MySQL).

- Human Resources (if outsourced): Developers, designers, trainers.

Procurement Process:

- Needs Identification: Conducted during the requirements phase.

- Soliciting Bids: Reach out to 3–5 vendors per item/service.

- Proposal Evaluation: Based on cost, reliability, compatibility, delivery time.

- Awarding Contracts: Chosen vendor signs contract including service level agreements.

- Vendor Oversight: Project Manager tracks deliveries and vendor performance.

Project Scope Management Plan

Scope control for the BrewCode POS project will be managed by the Project Manager. The project scope is established by the Scope Statement, Work Breakdown Structure (WBS) and WBS Dictionary. Project Manager and Cafe Owner/Client will collaborate to define and approve project scope documentation which comprises quality checklists against deliverables and work performance measures.

Suggested scope changes can be requested by the Project Manager, Client/Cafe Owner or any project team member. All changes to the project scope will be passed to the Project Manager, who will assess and review the change(s) requested. Upon acceptance, the Project Manager shall communicate the change to the Change Control Board and Customer/Café Owner for approval. Upon approval, Project Manager will update the project documents in question and notify all stakeholders of the changes made.Finally, the project deliverables and the project scope are accepted by the Café Owner/Client.

The Café Owner/Client formally accepts the project’s final deliverable, based on inspection of project documentation, testing results and all tasks and product functionalities are completed.

Quality Management Plan

The BrewCode POS project is dedicated to provide a high-quality Point-of-Sale (POS) system that fulfills the needs of small and medium-sized cafes. Quality management will verify that all project deliverables adhere to the formally specified acceptance standards. This section describes the roles, responsibilities, quality control, quality assurance, and monitoring techniques that will be used throughout the project's lifecycle.

1. Quality Roles and Responsibilities

- Project Sponsor (Café Owner)

  - Approves all quality standards for the BrewCode POS project.

  - Reviews all project tasks and deliverables for compliance with established quality requirements.

  - Signs off on the final project deliverable.

- Project Manager

  - Responsible for implementing the Quality Management Plan and ensuring compliance throughout the project.

  - Works with quality specialists to define and maintain quality standards.

  - Tracks and communicates all quality metrics to the project team and stakeholders.

- Quality Specialists (Testers & Developers)

  - Develop and implement quality control and assurance measures.

  - Define the tools and methodologies for tracking quality.

  - Maintain Quality Control and Assurance Logs throughout the project.

- Project Team (Developers, Designers, Trainers)

  - Ensure that all quality standards are met in their respective work areas.

  - Identify and communicate any quality-related concerns to the Project Manager.

2. Quality Control

Quality control for the BrewCode POS project involves systematic checks to ensure that all deliverables comply with approved quality standards. The process includes:

- Code Reviews: Ensuring best practices and adherence to coding standards.

- Automated and Manual Testing: Functional, performance, and security testing.

- Usability Testing: Ensuring that the POS interface is intuitive for café staff.

- Inventory and Payment Process Validation: Confirming seamless order processing.

The Project Manager and Quality Specialists will verify that all quality control measures are implemented and that any necessary corrections are made before deliverables are accepted.

3. Quality Assurance

Quality assurance ensures that the BrewCode POS project follows efficient and standardized development processes to minimize defects. The plan includes:

- Adherence to the Waterfall Process Model: Each phase is completed and reviewed before moving to the next.

- Requirement Traceability Matrix: Ensuring that all functional requirements are met.

- Code Documentation Standards: Ensuring maintainability and future scalability.

- End-User Feedback: Conducting user testing before deployment.

If any changes to the quality processes are required, the Project Sponsor must approve them before implementation. The Project Manager will then update the project documentation accordingly.

Risk Management Plan

The BrewCode POS project follows a structured approach to identifying and mitigating risks to ensure smooth development and deployment. The primary goal is to proactively identify risks and implement mitigation strategies before they impact the project.

1. Risk Identification & Assessment

Risks will be identified through:

- Initial stakeholder interviews.

- Competitor and market analysis.

- Technical feasibility studies.

Each risk will be evaluated based on its likelihood and impact on the project, and the most critical risks will be added to the project schedule for active monitoring.

2. Risk Mitigation Strategies

| Risk Category | Potential Risk | Mitigation Strategy |
| --- | --- | --- |
| Technical Risks | System bugs or integration failures. | Conduct extensive testing before deployment. |
| Financial Risks | Budget overruns. | Regular budget tracking and contingency fund allocation. |
| Operational Risks | Café staff struggling to adapt to the system. | Provide thorough training and user-friendly documentation. |
| Market Risks | Competition from existing POS providers. | Ensure unique selling points and customer-focused features. |
| Security Risks | Data breaches or payment failures. | Implement encryption, secure authentication, and compliance with payment security standards. |

| Risk Category | Potential Risk | Mitigation Strategy |
| --- | --- | --- |
| Technical Risks | System bugs or integration failures. | Conduct extensive testing before deployment. |
| Financial Risks | Budget overruns. | Regular budget tracking and contingency fund allocation. |
| Operational Risks | Café staff struggling to adapt to the system. | Provide thorough training and user-friendly documentation. |
| Market Risks | Competition from existing POS providers. | Ensure unique selling points and customer-focused features. |
| Security Risks | Data breaches or payment failures. | Implement encryption, secure authentication, and compliance with payment security standards. |

3. Risk Monitoring & Reporting

- Risk status updates will be provided during bi-weekly project meetings when risks are relevant.

- The Project Manager will track all identified risks and their mitigation efforts.

- If a risk materializes, an escalation plan will be executed, and adjustments will be made to minimize impact.

4. Post-Project Risk Review

At the end of the BrewCode POS project, the Project Manager will evaluate how effectively risks were managed and document lessons learned. This review will help improve risk management strategies for future projects.

### Resource Calendar

| Resource | Role | Week 1-2 | Week 3-4 | Week 5-6 | Week 7-8 |
| --- | --- | --- | --- | --- | --- |
| Project Manager | Oversight, scheduling | ✅ | ✅ | ✅ | ✅ |
| UI/UX Designer | Interface design | ✅ | ✅ | ❌ | ❌ |
| Backend Developer | Code, database | ❌ | ✅ | ✅ | ✅ |
| Tester | System testing | ❌ | ❌ | ✅ | ✅ |
| Trainer | Client training | ❌ | ❌ | ❌ | ✅ |

✅ = Active period
 ❌ = Not assigned/active

Schedule Management Plan

Objective:
 Manage the timely delivery of the BrewCode POS system using the Waterfall process.

Development Timeline:

| Phase | Timeline |
| --- | --- |
| Requirements & Design | Week 1–2 |
| Development (Core Features) | Week 3–4 |
| Testing and QA | Week 5–6 |
| Deployment & Training | Week 7–8 |

Schedule Control Strategy:

- Tracking Tools: Trello, Google Calendar, Gantt Chart.

- Progress Reviews: Weekly internal syncs, bi-weekly client demos.

- Milestones:

  - System Design Approved – End of Week 2

  - Feature Completion – End of Week 4

  - QA Testing Passed – End of Week 6

  - Deployed & Staff Trained – End of Week 8

- Change Management: All scheduling changes are documented and reviewed by the Project Manager. Major changes need client approval.

Cost Baseline

The cost baseline for the BrewCode POS project outlines the budget allocated to each phase of development, ensuring structured tracking and management of costs using earned value metrics.

| Project Phase | Budgeted Total (Hours) | Hypothetical Cost (₱50/hour) | Comments |
| --- | --- | --- | --- |
| Planning | 20-40 hours | ₱1000 - ₱2000 | Includes work hours for requirement gathering, initial client interviews, and project planning. Involves the project manager and initial research. |
| Design | 40-80 hours | ₱2000 - ₱4000 | Covers system architecture design, UI/UX wireframing (using Figma), and database structure setup. Involves designers and developers. |
| Coding | 80-120 hours | ₱4000 - ₱6000 | Development of core functionalities: order input interface, inventory updates, payment processing, and user access controls. Involves backend/frontend developers. |
| Testing | 40-60 hours | ₱2000 - ₱3000 | Includes rigorous testing with real transactions, bug fixes, and usability checks. Involves testers and developers. |
| Transition and Closeout | 20-40 hours | ₱1000 - ₱2000 | Deployment on café laptops, staff training, and final project documentation/handover. Involves trainers and the project manager. |

| Role | Member(s) | Responsibilities |
| --- | --- | --- |
| Project Manager | Assigned (unspecified) | Oversees the entire project timeline, monitors progress, facilitates communication. |
| UI/UX Designer | Assigned | Designs the wireframes and user interfaces; ensures café-friendly usability. |
| Backend Developer | Assigned | Implements core functionalities like order handling, payments, and inventory logic. |
| Tester | Assigned | Tests functionality, identifies bugs, ensures usability aligns with requirements. |
| Trainer | Assigned | Conducts training sessions for café staff after system deployment. |

| Item | Acceptable Level | Comments |
| --- | --- | --- |
| Performance | Orders should be processed within 2 seconds of input. The system should support at least 3 simultaneous users without lag. | Regular performance tests will ensure smooth operation. |
| Usability | The UI must be intuitive and user-friendly, requiring minimal training. At least 90% success rate in first-time user testing. | User Acceptance Testing (UAT) with café staff will validate ease of use. |
| Reliability | The system should maintain 99.5% uptime during business hours and handle at least 500 transactions per day. | Uptime monitoring and stress testing will be conducted. |
| Security | Role-based access must prevent unauthorized entry. All sensitive data must be encrypted and stored securely. | Security audits and penetration testing will be performed. |
| Accuracy | Sales and inventory updates must be 100% accurate with no discrepancies. | Regular data audits will verify transaction integrity. |
| Compliance | Must comply with local financial and data security regulations. | Compliance checks will be performed before deployment. |