West Visayas State University

College of Information and Communications Technology

Final Project in Systems Analysis and Design: BrewCode POS

Subtitle: "Brewing Efficiency: A POS That Puts Your Café in Control"

Ryan Cabalfin, Arthur John Pagayon, Zen Anthony Pastolero, Bonn Sasana, Selwyn Tambalo

BSCS 2 - A AI

I. System Overview

System Name: BrewCode POS
Tagline: Brewing Efficiency: A POS That Puts Your Café in Control

Overview:
BrewCode POS is a user-friendly Point of Sale system designed for small to medium-sized coffee shops. It simplifies order processing, automates payment and inventory tracking, and provides real-time insights for café owners. By minimizing manual entry errors and streamlining transactions, BrewCode POS helps coffee shops run efficiently and stay in control of daily operations.

II. Preliminary Investigation

SWOT Analysis

Strengths

- Streamlines order and payment processes.

- Real-time inventory updates.

- Role-based access control.

- Designed specifically for café environments.

Weaknesses

- Limited to laptop-based POS; no mobile version.

- No integration with accounting systems.

- Excludes loyalty programs.

Opportunities

- Could expand to mobile and tablet platforms.

- Potential to integrate with delivery apps and online ordering.

- Collaboration with local café businesses.

Threats

- Competition from established POS software.

- Technological changes requiring frequent updates.

- Resistance to digital systems from traditional café staff.

III. Feasibility Study

A. Operational Feasibility

- Fully supported by the café owner.

- Staff involvement during design and testing.

- Complies with the Data Privacy Act of 2012.

B. Technical Feasibility

- Developed using Visual Studio Code, Figma, and a local SQL database.

- Runs on laptops with internet access.

- Minimum specs: Dual-core processor, 4GB RAM, 1GB storage.

C. Schedule Feasibility

- 8-week development lifecycle using the Waterfall model.

D. Economic Feasibility

- Cost-effective: ₱10,000 - ₱17,000 overall budget.

- No third-party licensing costs.

- Uses open-source tools.

IV. Software Requirements

A. Requirements Analysis

Work Breakdown Structure (WBS)

| Level 1 | Level 2 |  | Level 3 |
| --- | --- | --- | --- |
| 1. Planning | 1.1 Requirements Gathering |  | 1.1.1 Client Interview 1.1.2 Site Analysis |
| 2. Design | 2.1 System Design |  | 2.1.1 UI Design (Figma) 2.1.2 Database Design |
| 3. Implementation | 3.1 Frontend Development |  | 3.1.1 POS Interface 3.1.2 User Login |
|  | 3.2 Backend Development |  | 3.2.1 Order Processing Logic 3.2.2 Inventory Management |
| 4. Testing | 4.1 Unit Testing |  | 4.1.1 Order Module 4.1.2 Inventory Module |
|  | 4.2 System Testing |  | 4.2.1 Integration Testing 4.2.2 Acceptance Testing |
| 5. Deployment | 5.1 Installation |  | 5.1.1 POS Setup in Café 5.1.2 User Onboarding |
| 6. Maintenance | 6.1 Bug Fixes |  | 6.1.1 Patch Updates 6.1.2 Support |

| TASK ID | DESCRIPTION | DURATION (DAYS) | PREDECESSOR |
| --- | --- | --- | --- |
| 1 | Gather requirements from stakeholders (staff, management, customers) | 4 days |  |
| 2 | Analyze current café workflows and technology | 3 days |  |
| 3 | Define functional and non-functional requirements | 3 days | 1, 2 |
| 4 | Design system architecture and interface sketches | 4 days | 3 |
| 5 | Develop order input interface | 4 days | 4 |
| 6 | Integrate inventory management system | 4 days | 5 |
| 7 | Add and configure payment processing module | 3 days | 6 |
| 8 | Test system with real transaction scenarios | 5 days | 7 |
| 9 | Perform user acceptance testing (UAT) | 3 days | 8 |
| 10 | Deploy system and perform staff training | 4 days | 9 |

Gantt Chart

goods, di na lang specific nga date

| Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements Gathering |  |  |  |  |  |  |  |  |
| Design (UI & DB) |  |  |  |  |  |  |  |  |
| Development (Frontend) |  |  |  |  |  |  |  |  |
| Development (Backend) |  |  |  |  |  |  |  |  |
| Testing |  |  |  |  |  |  |  |  |
| Deployment |  |  |  |  |  |  |  |  |

| Task | Week 1 |  | Week 2 |  | Week 3 |  | Week 4 |  | Week 5 |  | Week 6 |  | Week 7 |  | Week 8 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Requirements Gathering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Analyze Workflow |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Define Requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Design UI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop Order Input |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Integrate Inventory |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Add Payment Module |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Transaction Testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| User Test |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Deploy and Train Staff |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

PERT Chart

sala ni

| Letter | Task | Depends On | Duration (Expected) |
| --- | --- | --- | --- |
| A | Requirements Gathering | — | 3.33 days |
| B | UI Design | A | 3.00 days |
| C | Database Design | A | 2.17 days |
| D | Frontend Development | B | 4.00 days |
| E | Backend Development | C | 5.17 days |
| F | Testing | D, E | 3.00 days |
| G | Deployment | F | 2.00 days |

”Critical Path: A → C → E → F → G

Total Project Duration: = 15.67 days

Data Flow Diagram

Entity Relationship Diagram

Use Case

B. System Requirements

Functional Requirements

- Add, edit, and delete orders.

- View and update inventory in real-time.

- Process payments and generate receipts.

- Track order status (served/paid).

- Role-based access for owner and staff.

Non-functional Requirements

- Usability: Minimal training needed; intuitive UI.

- Security: Role-based login, secure database.

- Reliability: 99.5% uptime.

- Performance: Orders processed within 2 seconds.

- Availability: 24/7 access on café laptop.

- Scalability: Can scale to support more users if needed.

C. Conceptual and Logical Models

Data Flow Diagrams:

- Context Diagram

- Diagram 0 (High-Level View)

- Diagram 1+ (Detailed Modules)

Entity Relationship Diagram (ERD):

- Entities: User, Order, Item, Inventory, Payment

- Relationships: User-Order (1:M), Order-Item (M:M), Item-Inventory (1:1)

Class Diagram: [To be added based on ERD structure]

Use Case Diagram:

- Actors: Owner, Staff

- Use Cases: Login, Place Order, Process Payment, Manage Inventory

Flowchart:

- Illustrates flow from Home -> Order -> Payment -> Receipt

System Architecture:

- 3-tier architecture: UI layer, Logic layer, Data layer

V. Conclusion

BrewCode POS provides a practical, focused, and efficient solution tailored to small cafés. With robust functionality and minimal hardware requirements, it gives café owners greater visibility and control over operations while simplifying the workflow for staff. This documentation serves as a comprehensive blueprint for the development, implementation, and evaluation of the BrewCode POS system.